## Slide 1
Week 19 – Mon 16th September to Sun 22nd September
ORM 1 – Storage

## Slide 2
Page 1
Agenda
Open Actions Items
Incidents Trend Analysis/Insights
P1/P2 Incidents and Problem tickets
Completed Changes in Last week
Forward Schedule of Change
Infrastructure Compliance
Storage Firmware Upgrade Status
RFS Completed
Service Improvements
Migrated Volumes reclamation
New Risks and Existing Risks Progress Updates
Storage Capacity (CPW, Dixons, Polaris and CBS)
Delivery Achievements
Team Communication/Escalation Structure

## Slide 3
Page 2
Open Action Items
Reference ID | Description | Expected Outcome | Start Date | Raised by | Ownership | ETA | Status | Comments

## Slide 4
Page 3
Incidents Trend Analysis/Insights
Incidents - Service Quality | Week 17 | Week 18 | Week 19 | Week 20
Total No of incoming Tickets | 7 | 10 | 13 | 17
Total of Closed / Resolved Tickets | 5 | 10 | 10 | 17
Proactive tickets | 7 | 10 | 13 | 17
Reactive tickets | 0 | 0 | 0 | 0
Severity 1 & 2 | 0 | 0 | 0 | 0
Severity 3 & 4 | 7 | 10 | 10 | 17
Total SLA / SLO Missed Tickets | 0 | 0 | 0 | 0
Page 3
Page 3
Page 3
Page 3
Chart: INC
Chart: 
Chart: No. Of INCs
| Week 17 | Week 18 | Week 19 | Week 20
 | 7 | 10 | 13 | 17

## Slide 5
Page 4
P1/P2 Incidents and Problem tickets
P1/P2 Reference | Description | Resolution | Start/Finish Date and time | Problem Reference | Ownership | Problem Closure

## Slide 6
Page 5
Completed Changes (1 week)
Change Ref | Description | change | Start/Finish Time | Status

## Slide 7
Page 6
Forward Schedule Change (1 week)
Change Ref | Description | change type | Start/Finish Time | Comments
CRQ000000087987 | PROD: Performing code upgrade on GBFPSXSVC01 storage box to the version 7.8.1.10 | Normal | Start Time: 10/16/2019 11:00:00 PM End Time: 10/17/2019 6:00:00 AM | Waiting for SAM to Provide Feasible Dates & confirmation
CRQ000000087990 | PROD: Performing code upgrade on GBNPSXSVC01 storage box to the version 7.8.1.10 | Normal | Start Time: 10/23/2019 11:00:00 PM End Time: 10/24/2019 6:00:00 AM | Waiting for SAM to Provide Feasible Dates & confirmation
CRQ000000088043 | PROD: Ontap upgrade on NEMO Dixons NetApp Filers NA13 and NA14 | Normal | Start Time: 10/01/2019 00:00:00 AM End Time: 10/01/2019 8:00:00 AM | Still haven’t received approvals from the Business team.
CRQ000000088141 | PROD: To fix the security vulnerabilities APARS need to upgrade NetApp filers NA11 and NA12 to recommended patch version. | Normal | Start Time: 10/03/2019 00:00:00 AM End Time: 10/03/2019 8:00:00 AM | Still haven’t received approvals from the Business team
CRQ000000091153 | Data centre HWIP team to check the path/cabling between Juno and Apollo switches service : CPW_UK_File Services (CPW Central/PLC) | Normal | Start Time: 9/26/2019 21:00 End Time9/26/2019 23:00 | Under CAB Approvals

## Slide 8
Upgrades (To be covered under compliance)
Compliance
Page 7
Infrastructure Compliance

## Slide 9
Page 8
Firmware upgrade Status
Environment | Storage Device | Current Code | Target Code | Target Date
CPW | GBGPSXSTO02(V7000) | 7.8.1.8 | 7.8.1.10 | Completed (17-June-2019)
CPW | GBGPSXSTO03 (V7000) | 7.8.1.8 | 7.8.1.10 | Completed (17-June-2019)
CPW | GBNPSXSTO08 (V7000) | 7.8.1.8 | 7.8.1.10 | September 2019
CPW | GBNPSXSTO03 (V7000) | 7.8.1.8 | 7.8.1.10 | September 2019
CPW | GBNPSXSTO10 (V7000) | 7.8.1.8 | 7.8.1.10 | September 2019
CPW | GBNPSXSTO07 (V7000) | 7.5.0.13 | 7.8.1.10 | Completed (25-June-2019)
CPW | GBGPSXSTO01 (SAN80B) | 7.4.1d | 7.4.2d | Completed (10-April-2019 )
CPW | GBNPSXSTO01 (SAN80B) | 7.4.1d | 7.4.2d | Completed (20-Aug-2019)
CPW | GBNPSXSTO02 (SAN80B) | 7.4.1d | 7.4.2d | Completed (20-Aug-2019)
Dixons | L06V7K02 (V7000) | 7.5.0.13 | 7.8.1.10 | Completed(9-September 2019)
Dixons | L01V7K02 (V7000) | 7.5.0.13 | 7.8.1.10 | Completed 9-September 2019
Dixons | L6SVC02 (SVC) | 7.5.0.13 | 7.8.1.10 | Completed (9-September 2019)
Dixons | L01SVC02 (SVC) | 7.5.0.13 | 7.8.1.10 | Completed( 9-Sepe-2019)

## Slide 10
Page 8
Firmware upgrade Status
Environment | Storage Device | Current Code | Target Code | Target Date
Polaris | GBFPSXFCS01 (XIV) | 11.6.1.a | 11.6.2.a | Jan 2020
Polaris | GBNPSXFCS01 (XIV) | 11.6.1.a | 11.6.2.a | Jan 2020
Polaris | GBFPSXSVC01 (SVC) | 7.6.1.6 | 7.8.1.10 | September 2019
Polaris | GBNPSXSVC01 (SVC) | 7.6.1.6 | 7.8.1.10 | September 2019
Polaris | GBFPSXFCS01(SAN) | 7.4.1d | 7.4.2d | Completed (20-Aug-2019)
Polaris | GBFPSXFCS02(SAN) | 7.4.1d | 7.4.2d | Completed (20-Aug-2019)
Polaris | GBFPSXFCS03(SAN) | 7.4.1d | 7.4.2d | Completed (20-Aug-2019)
Polaris | GBFPSXFCS04(SAN) | 7.4.1d | 7.4.2d | Completed (20-Aug-2019)
Polaris | GBNPSXFCS01(SAN) | 7.4.1d | 7.4.2d | Completed (20-Aug-2019)
Polaris | GBNPSXFCS02(SAN) | 7.4.1d | 7.4.2d | Completed (20-Aug-2019)
Polaris | GBNPSXFCS03(SAN) | 7.4.1d | 7.4.2d | Completed (20-Aug-2019)
Polaris | GBNPSXFCS04(SAN) | 7.4.1d | 7.4.2d | Completed (20-Aug-2019)
Polaris | GBNPSXDS801(DS8870) | R7.5 bundle 87.51.93.5120 | 87.51.121.0 | Jan 2020
Notes: 10

## Slide 11
Page 9
Firmware upgrade Status
Environment | Storage Device | Current Code | Target Code | Target Date
CBS | GBFPCXV7K11 (V7000) | 7.8.1.8 | 7.8.1.10 | Completed
CBS | GBNPCXV7K11 (V7000) | 7.8.1.8 | 7.8.1.10 | Completed
CBS | Gbfpcxfcs05 (Cisco edge switch) | 6.2(9) | 8.3(1) | Completed
CBS | Gbfpcxfcs07 (Cisco edge switch) | 6.2(9) | 8.3(1) | Completed
CBS | Gbfpcxfcs06 (Cisco edge switch) | 6.2(9) | 8.3(1) | Completed
CBS | Gbfpcxfcs08 (Cisco edge switch) | 6.2(9) | 8.3(1) | Completed
CBS | Gbfpcxfcs01 (Cisco Core switch) | 6.2(11c) | 8.3(1) | Completed
CBS | Gbfpcxfcs02 (Cisco Core switch) | 6.2(11c) | 8.3(1) | Completed
CBS | Gbnpcxfcs05 (Cisco Edge switch) | 6.2(9) | 8.3(1) | Completed
CBS | Gbnpcxfcs07 (Cisco edge switch) | 6.2(9) | 8.3(1) | Completed
CBS | Gbnpcxfcs06 (Cisco edge switch) | 6.2(9) | 8.3(1) | Completed
CBS | Gbnpcxfcs08 (Cisco edge switch) | 6.2(9) | 8.3(1) | Completed
CBS | Gbnpcxfcs01 (Cisco Core switch) | 6.2(11c) | 8.3(1) | Completed
CBS | Gbnpcxfcs02 (Cisco Core switch) | 6.2(11c) | 8.3(1) | Completed

## Slide 12
Page 8
Firmware upgrade Status
Environment | Storage Device | Current Code | Acceptable Code | Target Date
Dixons | MDS10 (PCI) (Cisco switch) | 4.2(7e) | 6.2(13a) | Existing modules 2 out of 5 will not support upgrade to 5.x or 6.x
Dixons | MDS11 (PCI) (Cisco switch) | 4.2(7e) | 6.2(13a) | Existing modules 2 out of 5 will not support upgrade to 5.x or 6.x
Dixons | MDS12 (PCI) (Cisco switch) | 4.2(7e) | 6.2(13a) | Existing modules 2 out of 5 will not support upgrade to 5.x or 6.x
Dixons | MDS13 (PCI) (Cisco switch) | 4.2(7e) | 6.2(13a) | Existing modules 2 out of 5 will not support upgrade to 5.x or 6.x
Dixons | AMS2100_A | 08C3/F-X | 08E1/M | As this device will be decommissioned after migrations, we are not going for further upgrade.
Dixons | AMS2100_B | 08C3/F-X | 08E1/M | As this device will be decommissioned after migrations, we are not going for further upgrade.
Dixons | SHMSA01 | GL200P002 | GL220P009 | Kept on hold (Requested VMware and application teams 2-3 hours downtime for drive code upgrade)
Dixons | SHMSA02 | GL200P002 | GL220P009 | Kept on hold (Requested VMware and application teams 2-3 hours downtime for drive code upgrade)

## Slide 13
Page 10
RFS Completed
RFS Change no./ INC No. | Project or Requester | Description | Implementation Date

## Slide 14
Service Improvements
Serial Number | Description | Business benefit or value add | Owner | Target completion date | % completed
Page 10

## Slide 15
Migrated volumes reclamation
Page 11
Change N | Environment | Device name | Reclaimed Capacity (TB) | Date

## Slide 16
Risk to be raised
CPW | Dixons (PCI, Non PCI & Non – Prod) | Polaris
 | Dixons (PCI) - L01SVC02 L01V7K02 Dixons (NON-PCI) and (NON-PROD)--- These devices will be decommissioned after migration L01SVC01 L06SVC01 L06SVC03 | GBNPSXSVC01 GBFPSXSVC01
Currently CPW and Dixons(PCI) V7000's and SVC's storage devices running recommended version (7.5.0.13). Due to legacy hosts and hardware compatibility connected these storage devices, we are not recommended to upgrade to target version 7.8.1.8 or 7.8.1.10
End of life announced 30th Sept 2017 for AMS2100 devices (backend to L06SVC03 and L06SVC01). We have support for this devices and all the data has been migrated to new environment. List of devices AMS2100_A (backend to L06SVC03) AMS2100_B (backend to L06SVC01)
Page 13
End of life announced 30th Sept 2017 for V7000 Gen1 , SVC CG8 and CF8 and SAN80B List of devices applicable V7000 Gen 1: Gbnpsxsto08, Gbnpsxsto07, Gbnpsxsto03, Gbnpsxsto10, Gbgpsxsto02, Gbgpsxsto03, (CPW Environment: Citrix, PIE, PCI ) L01V7K02, L06V7K02 (Dixons backend Devices used for PCI environment) SVC CG8 : L01SVC02 , L06SVC02 (Dixons PCI) SAN 80B : Gbnpsxsto01, Gbnpsxsto02 and gbgpsxsto01 (CPW environment: Citrix , PIE)

## Slide 17
Risk to be raised
Capacity Constraints in Dixons PCI Storage Devices . PCI Storage Devices are L01SVC02 and L06SVC02
Capacity Constraints in CPW Storage Devices. GBNPSXSTO03 (V7000) services are CPW Citrix environment
Page 13

## Slide 18
Page 14
Existing Risk
Description | Consequence | Likelihood of happening | Mitigation
RISK No.669 Unsupported HP open VMS server on V7000(CPW) NHBR_07, NHBR_10 and GFORD_03 storage devices. | In case of any issues on HP Open VMS servers its difficult for us or TSS to troubleshoot and find out RCA | NA | No plans in place until VMS servers hardware is upgraded
RISK No.670 CISCO has already announced EOL of MDS 9509 switches | CISCO has already announced the EOL and EOS for the MDS 9509 SAN switches. The product will become EOS on April 30, 2019. | NA | Devices in Non PCI Will be decommissioned as part of Migration. But, devices in PCI will be lift and shift to new environment and Risk extended till 31st August 2018
RISK No.668 Performing firmware upgrade on V7000 gbnpsxsto07 storage | DCG gbnpsxsto07 would not be complaint with microcode recommendation provided by the storage community and further in case of any issues TSS or IBM Support team would also not support for troubleshooting | NA | No plans in place until VMS servers hardware is upgraded
RISK No.809 Storage capacity running above 90% for CPW NetApp Filers (gbnpsxsto05 & gbgpsxsto08) | Disruption to Business critical application services (CAT0. CAT1) and Storage provisioning will be difficult for future requests. | NA | Plan A- To delete the unwanted data from the volume , we are not sure Since the Customer wants all the data Plan B- To Add Additional Disk shelf to the existing fliers
RISK No.810 CPW NetApp Storage devices End of Life since 2013 and End of Support from 31st July 2018 | We’ll not get HW / SW support for the devices. | NA | Storage refreshment - Planning to migrate the NetApp storage data to another new Storage.

## Slide 19
Page 14
Existing Risk
Description | Consequence | Likelihood of happening | Mitigation
RISK No. 840 During the time of software related issues unable to get the support from the vendor(IBM TSS). | Potential threat: We would not get any technical support for root cause analysis, performance issues and software documentation...etc (no security threats as we are receiving APAR’s and CIRATS ) | NA | Need to purchase the software support for the devices to mitigate. Customer owned devices.
RISK No. 839 During the time of software related issues unable to get the support from the vendor(IBM TSS) | Potential threat: We would not get any technical support for root cause analysis, performance issues and software documentation...etc (no security threats as we are receiving APAR’s and CIRATS ) | NA | No update.

## Slide 20
SAN Capacity - CPW
Serial no. | Storage Array | Total Capacity (TB) | Allocated Capacity (TB) | Available Capacity (TB) | Status (% utilized)
1 | GBNPSXSTO08 (IBM V7000) | 10.35 | 8.80 | 1.55 | 85% (Allocating storage from Gbnpsxsto10)
2 | GBNPSXSTO07 (IBM V7000) | 26.69 | 18.26 | 8.46 | 68%
3 | GBNPSXSTO03 (IBM V7000) | 5.05 | 4.88 | 0.17 | 96% (Allocating storage from Gbnpsxsto10)
6 | GBNPSXSTO10 (IBM V7000) | 41.44 | 18.82 | 22.65 | 45%
4 | GBGPSXSTO02 (IBM V7000) | 28.62 | 23.84 | 4.78 | 83%
5 | GBGPSXSTO03 (V7000) | 26.69 | 22.56 | 4.15 | 85%
Page 15

## Slide 21
Page 16
NAS Capacity - CPW
Serial no. | Storage Array | Total Capacity (TB) | Allocated Capacity (TB) | Available Capacity (TB) | Status (% utilized)
1 | GBNPSXSTO04 (IBM N-Series) | 94 | 84 | 8 | 89%
2 | GBNPSXSTO05 (IBM N-Series) | 99 | 93 | 5 | 94%
3 | GBGPSXSTO07 (IBM N-Series) | 95 | 82 | 12 | 87%
4 | GBNPSXSTO08 (IBM N-Series) | 98 | 93 | 4 | 95%

## Slide 22
Page 17
SAN Capacity - Dixons
Serial no. | SAN Volume Controller | Total Capacity (TB) | Allocated Capacity (TB) | Available Capacity (TB) | Status (% utilized)
1 | L01SVC01 | 119.74 | 111.72 | 8.03 | 93%
2 | L06SVC01 | 121.01 | 99.99 | 21.02 | 83%
3 | L06SVC03 | 58.47 | 54.77 | 3.70 | 94%
4 | L01SVC02 | 21.41 | 20.97 | 0.44 | 98%
5 | L06SVC02 | 32.00 | 30.45 | 1.80 | 95%
6 | SHMSA01 | 14.4 | 13.67 | 0.73 | 94%
7 | SHMSA02 | 14.4 | 13.67 | 0.73 | 94%

## Slide 23
Page18
SAN Capacity - Dixons
SAN Volume Controller | Backend Storage Array | Total Capacity (TB) | Allocated Capacity (TB) | Available Capacity (TB) | % utilized (Physical) | % utilized (Virtual Allocation)
L06SVC03 | XIV | 24.70 | 22.98 | 1.55 | 91% | 114%
 | AMS2100_A | 6.25 | 4.69 | 1.56 | 72% | 115%
 | L06NETAPP (na01 and na02) | 27.51 | 28.85 | 0.6 | 93% | 135%
SAN Volume Controller | Backend Storage Array | Total Capacity (TB) | Allocated Capacity (TB) | Available Capacity (TB) | % utilized (Physical) | % utilized (Virtual Allocation)
L01SVC01 | L01VNX | 97.4 | 94.92 | 2.56 | 97% | 117%
 | L01VMAX B | 4.06 | 0.6 | 3.46 | 14% | 147%
 | L01VMAX A | 18.27 | 15.71 | 2.55 | 85% | 136%
L06SVC01 | L06VNX | 96.49 | 87.69 | 8.79 | 90% | 115%
 | L06VMAX-B | 18.27 | 9.23 | 9.02 | 50% | 71%
 | AMS2100B | 6.25 | 2.68 | 3.57 | 42% | 57%
L01SVC02 | L01V7K02 | 21.41 | 20.96 | 0.7 | 96% | 120%
L06SVC02 | L06V7K02 | 24.50 | 23.73 | 0.76 | 95% | 103%
 | L06V7K02_Backup | 7.50 | 6.71 | 0.8 | 89% | 99%
Notes: 23

## Slide 24
Page 19
NAS Capacity - Dixons
Serial no. | Storage Array | Total Capacity (TB) | Allocated Capacity (TB) | Available Capacity (TB) | Status (% utilized)
1 | NA11 (NetApp) | 47 | 32 | 15 | 68%
2 | NA12 (NetApp) | 47 | 24 | 23 | 51%
3 | NA13 (NetApp) | 34 | 27 | 6 | 79%
4 | NA14 (NetApp) | 34 | 22 | 12 | 65%

## Slide 25
Page 20
SAN Capacity–Polaris & Cloud Backup
Serial no. | Device name | Total Capacity (TB) | Allocated Capacity (TB) | Available Capacity (TB) | Status (% utilized)
1 | GBNPSXSVC01 (SVC) - Polaris | 446.06 | 383.97 | 62.09 | 86%
2 | GBFPSXSVC01 (SVC) - Polaris | 291.10 | 244.75 | 46.83 | 84%
3 | GBNPCXV7K11 (V7000) - CBS | 502.83 | 455.51 | 47.56 | 91%
4 | GBFPCXV7K11 (V7000)- CBS | 471.19 | 440.81 | 30.38 | 94%

## Slide 26
Page 21
SAN Capacity - Polaris
SAN Volume Controller | Backend Storage Array | Total Capacity (TB) | Allocated Capacity (TB) | Available Capacity (TB) | % utilized (Physical) | % utilized (Virtual Allocation)
GBNPSXSVC01 | GBNPSXXIV01_0 | 291.10 | 243.89 | 45.93 | 86% | 112%
 | GBNPSXDS801_300 GB | 48.71 | 34.83 | 13.82 | 71% | 106%
 | GBNPSXDS801_600 GB | 106.25 | 103.54 | 2.34 | 97% | 140%
GBFPSXSVC01 | GBFPSXXIV01_0 | 291.10 | 237.90 | 46.35 | 79% | 126%

## Slide 27
Page 22
Delivery Achievements (Monthly)

## Slide 28
Team contact details
NAS Team Details
SAN Team Details
NAS On Call Numbers +91-9582448877, +91-9538777357
Name | Contact Number | email
Kiran Kasavajhala (SME) | +91-8050915109 | kkasavaj@in.ibm.com
Venkata Sai Pani Kumar K | +91-9902267733 | vkothuri@in.ibm.com
Bala Subramanyam H K | +91-9629173222 | bahubra@in.ibm.com
Name | Contact Number | email
Prity Sharma | +91-9582448877 | pritysha@in.ibm.com
Bhaskara | +91-9538777357 | bpitchik@in.ibm.com
Page 23
SAN On Call Numbers +91-8050915109, +91-9902267733

## Slide 29
Thank you
Page 24